## Sheet1
Phase 1: Initial Development and Implementation | W 1 | W2 | W3 | W 4 | W 5 | W 6 | W 7 | W 8 | W 9 | W 10 | W 11 | W 12
Initiation and Planning
- Define project objectives, scope, milestones | bar: W 1
- Set up communication channels and tools | bar: W2
Literature Review
- Gather sources on mesoscale modeling, alloys | bar: W3 to W 4
Model Selection and Formulation
- Choose a numerical modeling approach | bar: W 4 to W 5
- Formulate governing equations and rules | bar: W 5 to W 6
Initial Implementation
- Begin coding model based on formulated rules | bar: W 6 to W 8
Basic Simulations
-Verify the correctness of the model through simulations | bar: W 8 to W 10

## Sheet2
Phase 2: Model Refinement and Analysis | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Model Refinement and Calibration
- Collect experimental data for calibration | bar: W1 to W2
- Adjust model parameters to match data | bar: W3 to W4
Comprehensive Simulations
- Simulate microstructural evolution in alloys | bar: W5 to W8
Sensitivity Analysis
- Investigate the effects of parameters on outcomes | bar: W7 to W10
Reporting and Documentation
- Draft final project report | bar: W10 to W12
- Document model development, simulations | bar: W11 to W12
- Prepare a presentation summarizing the findings | bar: W12