## Sheet1
Phase 1: Initial Development and Implementation | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Initiation and Planning
- Define project objectives, scope, milestones | bar: Week 1
- Set up communication channels and tools | bar: Week 2
Literature Review
- Gather sources on mesoscale modeling, alloys | bar: Week 3 to Week 4
Model Selection and Formulation
- Choose a numerical modeling approach | bar: Week 4 to Week 5
- Formulate governing equations and rules | bar: Week 5 to Week 6
Initial Implementation
- Begin coding model based on formulated rules | bar: Week 6 to Week 8
Basic Simulations
-Verify the correctness of the model through simulations | bar: Week 8 to Week 10

## Sheet2
Phase 2: Model Refinement and Analysis | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Model Refinement and Calibration
- Collect experimental data for calibration | bar: Week 1 to Week 2
- Adjust model parameters to match data | bar: Week 3 to Week 4
Comprehensive Simulations
- Simulate microstructural evolution in alloys | bar: Week 5 to Week 8
Sensitivity Analysis
- Investigate the effects of parameters on outcomes | bar: Week 7 to Week 10
Reporting and Documentation
- Draft final project report | bar: Week 10 to Week 12
- Document model development, simulations | bar: Week 11 to Week 12
- Prepare a presentation summarizing the findings | bar: Week 12